## User Guide
A free template brought to you by:
Gantt Chart User Guide
Overview
This template allows you to manage your multi-phase project by keeping track of tasks, status, and dependencies It provides easy visualization of important and dependent tasks to maximizing your teams productivity. The template includes:
Example Template | Filled in template with sample tasks, team members, and dependencies
Blank Template | Blank template ready to be filled in manually and with dropdown buttons
Project Options | Table that allows you to change common tags to be used in the template
Template
This template includes the following fields for easy project management:
Index | Index of the task in the phase and project overall
Task Name | Name of the task
Status | Current status of the task inputted with dropdown menu (customized in "Project options")
Priority | Current priority level (customized in "Project Options")
Start Date | Start date of a task
Deadline | Expected deadline for a task (must be after "Start Date")
Team Members | Team member assigned to the task (customized in "Project options")
Completion (%) | Percent completion of a task
Total Completion | Tracks the total phase completion based on task completion
Overall Completion | Tracks the entire project completion based on phase completion
Project Options
This section allows you to change common tags to be accesed in a dropdown menu for certain categories. To change tag names, simply input a new name in a cell marked "--" or replace the names that we have populated the options with.

## Example Template
A free template brought to you by:
Gantt Chart Example Template
[7 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Index | Task Name | Status | Start Date | Deadline | Team Member | Completion (%)
1.1 | Brainstorm Marketing Strategy | Completed | 2020-03-01 | 2020-03-02 | Emily | 100% | bar: Week 1 M to Week 1 T
1.2 | Mockup App Design | Completed | 2020-03-02 | 2020-03-04 | Rajesh | 100% | bar: Week 1 T to Week 1 R
1.3.1 | Meet with Stakeholders | Completed | 2020-03-05 | 2020-03-09 | Isabella | 100% | bar: Week 1 F to Week 2 T
1.3.2 | Finalize Team Members | Completed | 2020-03-08 | 2020-03-10 | Isabella | 100% | bar: Week 2 M to Week 2 W
1.4 | Product Design Sprint | Completed | 2020-03-11 | 2020-03-12 | Emily | 100% | bar: Week 2 R to Week 2 F
1.5.1 | Framework Creation | Completed | 2020-03-15 | 2020-03-17 | Gus | 100% | bar: Week 3 M to Week 3 W
1.5.2 | Debugging | Completed | 2020-03-16 | 2020-03-19 | Riya | 100% | bar: Week 3 T to Week 3 F
[5 empty] | Total Completion | 100%
Index | Task Name | Status | Start Date | Deadline | Team Member | Completion (%)
[5 empty] | Total Completion | #DIV/0!
Index | Task Name | Status | Start Date | Deadline | Team Member | Completion (%)
[5 empty] | Total Completion | #DIV/0!
Index | Task Name | Status | Start Date | Deadline | Team Member | Completion (%) | bar: Week 10 M
[5 empty] | Total Completion | #DIV/0!
|  |  |  | OVERALL COMPLETION |  | #DIV/0!

## Blank Template
A free template brought to you by:
Gantt Chart Example Template
[7 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Index | Task Name | Status | Start Date | Deadline | Team Member | Completion (%)
[5 empty] | Total Completion | #DIV/0!
Index | Task Name | Status | Start Date | Deadline | Team Member | Completion (%)
[5 empty] | Total Completion | #DIV/0!
Index | Task Name | Status | Start Date | Deadline | Team Member | Completion (%)
[5 empty] | Total Completion | #DIV/0!
Index | Task Name | Status | Start Date | Deadline | Team Member | Completion (%) | bar: Week 10 M
[5 empty] | Total Completion | #DIV/0!
|  |  |  | OVERALL COMPLETION |  | #DIV/0!

## Project Options
A free template brought to you by:
Project Options
Edit what common options you would like in your dropdown menu for certain cells
Status | Prioritiy | Team Members
Not yet Started | High | Emily
On Hold | Medium | Rajesh
In Progress | Low | Isabella
Debugging | -- | Gus
Completed | -- | Riya
-- | -- | --
-- | -- | --
-- | -- | --