## User Guide
A free template brought to you by:
Resource Management User Guide
Overview
This template allows you to manage your resources by keeping track of tasks, estimated hours, and hour breakdown by team member. It provides easy sorting of priority tasks or upcoming deadlines to maximizing your teams productivity. The template includes:
Example Template | Filled in template with sample tasks and resource allocation
Blank Template | Blank template ready to be filled in manually and with dropdown buttons
Project Options | Table that allows you to change common tags to be used in the template
Template
This template includes the following fields for easy task management:
Task Name | Name of the task
Status | Current status of the task inputted with dropdown menu (customized in "Project options")
Priority | Current priority level (customized in "Project Options")
Start Date | Start date of a task
Deadline | Expected deadline for a task (must be after "Start Date")
Hours | Hours expected to complete Task
Team Members | Name of each team member and their hour contribution to a task (names customized in "Project options")
Member Total | Total hours a team member is estimated to work for a project
Project Options
This section allows you to change common tags to be accesed in a dropdown menu for certain categories. To change tag names, simply input a new name in a cell marked "--" or replace the names that we have populated the options with.

## Example Template
A free template brought to you by:
Resource Management Example Template
Team Members
Task Name | Status | Priority | Start Date | Deadline | Hours | Rajesh | Emily | Isabella | Gus | Riya | -- | -- | --
Document HTML Code | Not yet Started | Low | 2020-03-01 | 2020-03-04 | 10 | 1 | 6 |  |  | 3
Contact Customer Support | On Hold | Low | 2020-04-23 |  | 3 |  |  | 2 | 1
Brainstorm front-end templates | In Progress | Medium | 2020-06-05 | 2020-06-30 | 15 | 5 | 2 | 1 | 1 | 6
New Mailing System | Debugging | High | 2020-07-02 | 2020-07-14 | 15 | 10 | 2 |  |  | 3
New Logo | In Progress | High | 2020-07-05 | 2020-08-03 | 20 |  |  | 10 | 10
|  |  |  | Member Total |  | 16 | 10 | 13 | 12 | 12 | 0 | 0 | 0

## Blank Template
A free template brought to you by:
Resource Management Example Template
Team Members
Task Name | Status | Priority | Start Date | Deadline | Hours | Rajesh | Emily | Isabella | Gus | Riya | -- | -- | --
|  |  |  | Member Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Project Options
A free template brought to you by:
Project Options
Edit what common options you would like in your dropdown menu for certain cells
Status | Prioritiy | Team Members
Not yet Started | High | Emily
On Hold | Medium | Rajesh
In Progress | Low | Isabella
Debugging | -- | Gus
Completed | -- | Riya
-- | -- | --
-- | -- | --
-- | -- | --