## Sheet1
Task | Start date | End date | Duration | Budget | Task owner | status | 5/1 | 5/2 | 5/3 | 5/4 | 5/5 | 5/8 | 5/9 | 5/10 | 5/11 | 5/12 | 5/15 | 5/16 | 5/17 | 5/18 | 5/19 | 5/22 | 5/23
Keyowrd research
Create an Excel sheet | 2023-05-01 | 2023-05-01 | 0 |  | Eddie | Completed
Use GKP to find kewyords | 2023-05-02 | 2023-05-03 | 1 |  | Eddie | Completed
Search Google to find competion | 2023-05-03 | 2023-05-04 | 1 |  | Eddie | Doing
Shortlist keywords to target | 2023-05-05 | 2023-05-05 | 0 |  | Eddie | Not Started
Create landing pages
Create page layout | 2023-05-01 | 2023-05-03 | 2 |  | Dilip | Completed
Select images to use | 2023-05-03 | 2023-05-03 | 0 |  | Dilip | Doing
Write copy for the page | 2023-05-08 | 2023-05-12 | 4 |  | Dilip | Not Started
Create and publish the page | 2023-05-15 | 2023-05-17 | 2 |  | Dilip | Not Started
Test the page | 2023-05-18 | 2023-05-19 | 1 |  | Megha | Not Started
Create campaigns
Write Ad headline & variations | 2023-05-10 | 2023-05-10 | 0 |  | Alex | Not Started
Write Ad copy & variations | 2023-05-11 | 2023-05-12 | 1 |  | Alex | Not Started
Create image to use in the ads | 2023-05-15 | 2023-05-15 | 0 |  | Rose | Not Started
Set up campaign in Google Ads | 2023-05-19 | 2023-05-19 | 0 |  | Alvin | Not Started
Start and track campaigns
Start the campaigns | 2023-05-22 | 2023-05-22 | 0 |  | Alvin | Not Started
Track CTR, CPC and conversions | 2023-05-23 | 2023-05-26 | 3 |  | Alvin | Not Started
Compare ad variations | 2023-05-29 | 2023-05-29 | 0 |  | Alvin, Virat | Not Started
A/B test landing page | 2023-05-30 | 2023-06-02 | 3 |  | Alvin, Virat | Not Started